BYT Website Build

Process Learnings — Astro/Sanity Phase

Better You Therapy LLC  ·  getbetteryou.com  ·  May 2026

Prepared by: CMO Agent  ·  Status: Internal Reference

Companion to: BYT_Process_Learnings_v3.docx (Relume/Figma Phase)

PURPOSE OF THIS DOCUMENT This document captures every process failure identified during the Astro/Sanity website build phase — specifically the gap between working HTML prototypes designed in Claude.ai and the broken production site delivered by Claude Code. It exists so these failures are not repeated on any remaining page build or future project.

# 1. Context — What Happened

Seven HTML prototype pages were designed and approved in Claude.ai. Each is a complete, standalone web page — all CSS inline, all JS embedded, rendering correctly when opened in any browser.

Claude Code (CC) was tasked with building a production site using Astro 6 + Sanity v4 + Cloudflare Pages. CC decomposed the working HTML files into Astro components, Sanity schemas, scoped CSS modules, and separate JavaScript files.

The result: all 7 pages were visually broken. No animations. Missing sections. Wrong typography, colors, spacing, and layout structure. The Sanity content seeding worked (correct text appeared), but the rendering layer failed completely.

Multiple rounds of deviation reports and targeted fixes failed to close the gap. The resolution was to abandon the decomposition approach entirely and inject the raw HTML directly into Astro pages, replacing only hardcoded text and image values with Sanity query variables.

# 2. Obstacle Log

Every obstacle identified during this phase, with severity and resolution status.

| # | OBSTACLE | DESCRIPTION | SEVERITY | STATUS |
| --- | --- | --- | --- | --- |
| OBS-001 | Sanity token deleted | Editor token was deleted when Deploy Studio token was created. Blocked all content seeding. Required Igor to manually create a new token in Sanity dashboard. | P0 | RESOLVED |
| OBS-002 | Astro decomposition failure | CC decomposed working HTML files into Astro components + Sanity schemas + scoped CSS + separate JS modules. Every page rendered broken: wrong layouts, missing styles, no animations, empty blocks. | P0 | RESOLVED |
| OBS-003 | IntersectionObserver dead (G4) | fade-up IntersectionObserver never attached on homepage. Entire page below the fold stuck at opacity:0. Same .forEach() attachment bug from the HTML build phase. | P0 | RESOLVED |
| OBS-004 | Container width wrong (G1) | Container set to 1280px instead of design-source 1200px. Affected all pages. | P2 | RESOLVED |
| OBS-005 | Base font-size wrong (G2) | Base font-size 16px instead of design-source 15px. Affected all pages. | P2 | RESOLVED |
| OBS-006 | Lora font not loaded (G7) | Lora serif font never loaded. Broke italic hero typography on Patients page. | P1 | RESOLVED |
| OBS-007 | Built all 7 pages at once | CC was told explicitly to build one page at a time. Built all 7 simultaneously. All were broken. Had to revert and restart page by page. | P1 | RESOLVED |
| OBS-008 | 30-min token burn on file copy | CC spent 30+ minutes and 50K tokens debugging Cloudflare deployment tokens to serve a single static HTML test file. Should have been a 3-command task: cp to public/, commit, push. | P2 | RESOLVED |
| OBS-009 | CSS specificity override | global.css .btn rule set border: 1.5px solid transparent, overriding visible borders on Apply Now buttons in Providers page. Required specificity bump to .btn.btn-secondary. | P1 | RESOLVED |
| OBS-010 | Missing page sections | Multiple entire sections missing across all pages: provider tags block (homepage), .l16 section (communities), hero dot overlay (providers), all CSS for careers page. | P0 | RESOLVED |
| OBS-011 | DOM structure changes | CC changed semantic elements (e.g., <a> to <div> on patient cards), swapped column order (contact page hero), changed grid columns (about page), changed width percentages (provider tracks). | P1 | RESOLVED |

# 3. Root Causes

The 11 obstacles share five underlying root causes.

| # | ROOT CAUSE | OBSTACLES CAUSED |
| --- | --- | --- |
| RC-1 | Interpreted HTML as content reference, not build spec | CC treated the design-source HTML files as a content guide to extract text from, not as pixel-perfect build specifications to reproduce. This caused OBS-002, OBS-004, OBS-005, OBS-006, OBS-010, OBS-011. |
| RC-2 | Applied conventional architecture without checking fit | CC followed Astro best practices (componentize everything, separate concerns) without verifying the output matched the source. Nobody told it not to decompose. The handoff doc said 'build 7 pages' and CC interpreted that as 'architect from scratch.' OBS-002. |
| RC-3 | Ignored explicit sequencing instructions | Prompt said 'one page at a time, wait for confirmation.' CC built all 7 simultaneously. OBS-007. |
| RC-4 | Over-engineered simple operations | A static file copy (cp + git push) became a 30-minute token-debugging session because CC tried to trigger deploys via API instead of using the auto-deploy pipeline. OBS-008. |
| RC-5 | Global CSS not audited against page CSS | CC extracted some styles to global.css without checking for specificity conflicts with page-level styles. OBS-009. |

# 4. Failed vs. Working Approaches

For each major problem area, the approach that failed and the approach that worked.

| PROBLEM | FAILED APPROACH | WORKING APPROACH |
| --- | --- | --- |
| Reproduce HTML designs in Astro | Decompose HTML into Astro components, Sanity schemas, scoped CSS, separate JS modules. Reinterpret layout through component boundaries. | Raw HTML injection. Copy full <body> content from design-source HTML into .astro file. Keep all styles and scripts intact with is:inline. Only replace hardcoded text with Sanity query variables. |
| Verify HTML files work | Create .astro page that renders the HTML through Astro pipeline. Debug for 30 minutes. | Copy HTML file to public/ directory. Astro serves it as static file with zero processing. 3 commands. |
| Build 7 pages | Build all simultaneously, deploy, hope they all work. | Build one page. Deploy. Confirm visual parity. Then next page. |
| CMS editability | Decompose everything into Sanity schemas and reconstruct via queries. | Keep HTML structure intact. Replace only text strings and image src values with Sanity variables. Layout/styles/scripts stay as raw HTML. |
| Button border visibility | Let global.css set border: transparent on all .btn elements. | Use higher-specificity selector (.btn.btn-secondary) to override global reset where visible borders are required. |

# 5. Rules for Remaining Pages

These rules govern all remaining page builds. They must be included in every CC prompt for this project.

| # | RULE | RATIONALE |
| --- | --- | --- |
| 1 | Design-source HTML files are build specs, not content references | The HTML files are complete, working web pages. They render correctly in a browser. CC's job is to serve them, not rewrite them. Every CSS value, class name, DOM structure, and script must be reproduced exactly. |
| 2 | Raw HTML injection is the build method | Copy everything between <body> and </body> into the .astro page. Keep all <style> and <script> tags. Use is:inline on scripts. The ONLY allowed modifications: replace hardcoded text/image values with Sanity variables. |
| 3 | One page at a time with confirmation gates | Build one page. Deploy. Wait for Igor's visual confirmation. Do not start the next page until the current one is confirmed. No exceptions. |
| 4 | Never rename classes, move styles, or restructure DOM | If the design-source uses a class name, you use that class name. If it uses inline styles, you keep inline styles. If it uses a specific DOM structure, you keep that structure. |
| 5 | Test with public/ before .astro | When verifying that an HTML file works, copy it to public/ and serve it as a static file. If it renders correctly there, any deviation in the .astro version is something CC introduced. |
| 6 | Use auto-deploy, not API triggers | Push to main. Cloudflare auto-deploys. Do not debug deployment tokens, poll deployment status, or manually trigger builds. |
| 7 | Audit global.css against page styles before deploying | After adding any page, check that global.css rules do not override page-specific styles via specificity. Diff the two and resolve conflicts before commit. |
| 8 | Sanity manages content, not layout | Sanity stores editable text and image references. It does not store layout, styles, animations, or structure. Those live in the .astro file as raw HTML from design-source. |

# 6. Timeline of Key Events

Phase 4 Complete (code): All 7 Astro pages built, Sanity schemas created, 21 schemas defined. Build passes. But all pages blank — Sanity singletons never seeded.

Sanity Token Blocker: Editor token deleted by mistake. New token required from Igor. Content seeding blocked until resolved.

Content Seeded: All 7 page singletons POSTed to Sanity. Hero copy confirmed on all routes. Nav and footer render from siteSettings.

Visual Inspection: All 7 pages visually broken. No resemblance to HTML prototypes. Deviation report produced: 7 cross-cutting issues + per-page failures across all routes.

Fix Attempt 1 — Targeted Fixes: CC given deviation report and told to fix. IntersectionObserver, container width, font-size, Lora font addressed. Per-page fixes attempted. Still broken.

Fix Attempt 2 — Raw HTML Injection (Prompted): Directive changed: stop decomposing, inject raw HTML. CC still created .astro rendering pipeline instead of static file test.

Fix Attempt 3 — Static File Test: Simplified to: copy HTML to public/test.html, push, verify. Proved HTML files work perfectly. Confirmed all deviations were introduced by CC's translation layer.

Homepage Built (Raw HTML): First page built using raw injection method. Deployed. Still broken — CC modified the HTML during injection.

Communities Built: Second attempt with stricter prompt. Deployed. Confirmed visual parity.

Providers Built: Third page. Button border issue found (OBS-009). Fixed with specificity bump. Confirmed.

Patients: In progress. Building with same raw injection method.

Remaining: About, Careers, Contact still pending. One at a time with confirmation gates.

# 7. Cost of Failure

The decomposition approach consumed approximately 3 full CC sessions before being abandoned. Each session involved extensive debugging, multiple deploy cycles, and detailed deviation analysis — none of which produced a working page.

The raw HTML injection approach produced a working, visually confirmed page in a single prompt cycle. The time ratio between the failed and working approaches is approximately 10:1.

The root lesson: when the input is a working, tested artifact, the fastest path to production is to use it as-is and modify minimally — not to reverse-engineer it into a different architecture.

# 8. Relationship to Process Learnings v3

BYT_Process_Learnings_v3.docx covers the Relume/Figma/HTML design phase — 11 misses related to wireframe interpretation, content flow application, and HTML build methodology.

This document covers the next phase: taking those approved HTML files and deploying them to production via Astro/Sanity/Cloudflare. The failures are different in nature — v3 was about building the right HTML, this document is about not destroying it during deployment.

Together, these two documents form the complete process learnings record for the BYT website build.